# Table of deliverables
## Phase 1: March 2021 to October 2021

Deliverable	Detail	Timelines	Success	Owner	Goals
Organisations to articulate their vision of and commitment to user engagement.	Influence senior leaders to promote and endorse the user engagement strategy for statistics by articulating their organisational commitment to user engagement. Best Practice and Impact (BPI) will collate a summary of each organisation’s ambitions for improving user engagement to share with the user engagement champion network.	March 2021 to May 2021	Departments owning and sharing their visions for effective user engagement via the user engagement champions network.	National Statistician, / Heads of Profession for statistics, / BPI	Culture
Identify and join-up existing user engagement initiatives.	Building on existing research, review user engagement activities to identify areas that the USER hub can support. Have a full understanding of what user engagement initiatives are being carried out by organisations producing official statistics and link these up to minimise duplication and maximise efficiency.	March 2021 to October 2021	Produce a baseline report highlighting current user engagement activities and identifying areas for improvement. / Share the characteristics of successful activities and user groups. / Publish information on the Government Statistical Service(GSS) website of engagement activities being carried out by producers of official statistics and highlight how these have been linked together to create efficiencies.	BPI	Capability
Publish case studies highlighting effective and successful engagement activities on the GSS website.	Case studies will show a range of engagement activities from wide-reaching user consultations to light-touch engagement. Examples will draw on UK and international best practice.	March 2021 and ongoing	Source and publish at least three new case studies on the GSS website each quarter.	BPI, / User engagement champions	Capability
Support and develop the user engagement champions network.	User engagement champions are an organisation’s point of contact on user engagement for statistics. Champions share best practice and guidance and support the strategy’s implementation. Organisations should nominate a user engagement champion to represent them if they have not done so already. Champions will be responsible for gathering organisational-level information on user experiences and user insights to share across the network.	March 2021 and ongoing	All organisations producing official statistics to have a nominated user engagement champion to represent them. / An active network of champions who engage with each other via ‘champion chats’. / Annual survey of champions to get an indication of whether the network is realising benefits for their department.	BPI, / User engagement champions, / Heads of Profession for statistics	Collaboration
Advertise existing user forums centrally.	There are already networks that bring together users of statistics. Work needs to be done to review the inclusivity of current user forums and ensure that these are centrally advertised so all producers and users of statistics have access to this information and can register an interest to attend.	April 2021 and ongoing	Central list of active user groups and forums, updated on an ongoing basis, published on the GSS website.	BPI	Collaboration
Explore governance options for strategically overseeing the work of new and existing theme-based user forums.	The work of new and existing theme-based user forums will need to be managed at a strategic level to avoid duplication and maximise use and impact. The cross-government Analysis & Evaluation Committee will need to agree governance options before they are implemented.	March 2021 to June 2021	BPI to present governance options to the Analysis & Evaluation Committee that consider existing user forums and networking initiatives.	BPI	Collaboration
Update induction training on user engagement.	Prepare slides that summarise the vision, goals and expectations of the user engagement strategy. Deliver these at the Government Statistician Group (GSG) induction sessions and promote their wider use across other organisations.	March 2021 to May 2021	Expectations for user engagement are delivered as part of the Government Statistician Group (GSG) and Office for National Statistics (ONS) induction training. / Circulate updated induction slides for use by other organisations.	BPI	Capability

## Phase 2: July 2021 onwards

Deliverable	Detail	Timelines	Success	Owner	Goal
Update and deliver necessary training and guidance to support the implementation of the user engagement strategy.	The USER hub will help producers of statistics to develop the knowledge, skills and techniques to address a variety of user needs. This will include updating existing guidance on user engagement and provide a toolkit of support for different engagement activities.	July 2021 and ongoing	Evidence of actively promoting the support services of the USER hub across government and updating user engagement guidance by October 2021.	USER hub	Capability
Provide a user engagement consultancy and mentoring service for analysts across government.	Set up a central consultancy service to provide practical advice to help support and deliver organisations’ engagement activities. Organise mentoring opportunities to build capability and encourage collaboration in carrying out wider user engagement.	July 2021 and ongoing	Pilot mentoring and consultancy services with at least two organisations by January 2022. Assess the impact of these interventions via a satisfaction survey.	USER hub	Capability
Ensure that strategic governance is set up to maintain standards and coordinate theme-based user engagement.	Following on from deliverable 1.6 promote the Analysis & Evaluation Committee’s preferred governance option for theme-based user forums and help recruit a diverse membership.	July 2021 to September 2021	A first meeting of the new governance board held by September 2021 and a schedule of further meetings agreed.	USER hub	Collaboration / Culture
Promote a cross-GSS approach to horizon scanning to anticipate future needs on new and emerging topics, themes and policy priorities.	The USER hub will work with ONS leaders to take forward horizon scanning work on behalf of the Analysis and Evaluation (A&E) committee. They will do this by engaging with users of statistics in a coordinated way, scanning for emerging debate and using engagement opportunities in forthcoming calendar events. They will link up existing user forums and programmes of coherence work and use innovative approaches to collaborate with partners from across the analytical community to recommend priority areas of work to the A&E committee.	July 2021 to December 2021	A coordinated programme of cross cutting priorities identified and agreed by the A&E committee. / Evidence of joined up data and activity across government and beyond to tackle priority cross-cutting areas. / Evidence of co-ordinating forum activity with wider GSS coherence work.	USER hub	Collaboration
Work with the Government Communication Service (GCS) to explore options for continuing to encourage the visibility of statisticians and include examples of this as part of a new toolkit.	Document, promote and share success stories. Highlight the impact that the visibility of producers of statistics has had to wider understanding of statistics and improved interaction and relationships with users of statistics (including the media).	July 2021 and ongoing	Preliminary discussions established with GCS setting out an ambition to formalise a GSS and GCS protocol regarding producers of statistics interacting more visibly via different platforms such as social media. / Top tips for increased visibility of producers of statistics included in a newly launched toolkit for user engagement.	USER hub	Capability / Culture

## Phase 3 – January 2022 onwards

Deliverable	Detail	Timelines	Success	Owner	Goal
Publish an organisational level statement of commitment to user engagement.	Organisations should set out how they have been and will be delivering against their vision outlined in deliverable 1.1.	March 2022 to June 2022	Published statements highlighting the range of engagement activities conducted and the opportunities on offer to encourage effective two-way engagement.	Heads of Profession for statistics	Collaboration / Culture
Measure progress of the implementation of the strategy’s goals.	Organisations to document their progress against the deliverables set out in the user engagement strategy including their commitments outlined in deliverable 3.1.	June 2022 to February 2025	USER hub to submit a report to the Public Administration and Constitutional Affairs Committee (PACAC) on an annual basis, outlining satisfactory progress towards the strategy’s vision, goals and deliverables.	User engagement champions, USER hub	Culture
Share actions and outcomes of user engagement activities.	In line with the Code of Practice for Statistics, producers of statistics should be transparent about the actions and outcomes of their engagement activities to enable users to understand how their feedback has been considered or actioned.	Jan 2022 and ongoing	Evidence of organisations using a range of mechanisms to feed back to users of statistics. This could be in the form of a ‘you said’, ‘we did’ notification.	Producers of statistics	Collaboration
Embed a user engagement objective into personal objectives.	Optional accountability objective for managers and individuals to add into personal objectives if working on statistical production. Ask all user engagement champions to trial the additional objective. Conduct baseline survey of current engagement activity.	April 2022 – October 2022	Evidence of increased user engagement activity amongst user engagement champions who have adopted the new objective. This will be measured every 6 months following introduction of the additional personal objective.	User engagement champions	Culture
Producers of statistics to be more visible to a wider audience.	Producers of statistics to appropriately use the USER hub’s toolkit to make themselves more accessible to a broader range of users. This could include taking steps to engage on social media or with different users in alternative forums.	April 2022 and ongoing	Evidence shared with user engagement champions to highlight the use of a range of techniques to reach and engage different audiences and an assessment of the impact this has had.	Producers of statistics	Capability